## Sheet1
SCHEDULE | USER STORIES | PRIORITY | ESTIMATED TIME | COMPLETE? | MILESTONES | COMPLETED BY
WEEK 4 | As a User I want to be able to sign up and create my own account so that when I log back in my credentials are still there | Highest | 2 Days | Yes | Login/Sign up working | WEEK 4
| As a User I want to be able to Logout by clicking the Logout button so that I am redirected back to the login screen | Highest | 1-3 Days | Yes | User can update classes which will be put onto Parse | WEEK 5
WEEK 5 | As a User I want to be able to type in my classes so that they are added to my User. | Highest | 1-3 Days | Yes | User can start matching with other users via swipping and profiles shown will be based on a Matching algorithm based on number of classes | WEEK 6
| As a User I want to be able to click the image which will redirect me to my gallery so that I can choose which image I want to represent myself | Highest | 1-3 Days | Yes | User can update images to Parse | WEEK 7
| As a User I want to be able to relog in and see the previously updated classes and image so that I will no have to fill them in again | Highest | 1-3 Days | Yes | Swipping right will upload the other user's ID and you can view your matched profiles | WEEK 7
WEEK 6 | As a User I want to be able to display a profile of my own classes that I am currently taking so that other students can match with me | Highest | 1 Day | Yes | Users can message matched users. Previous conversations will be stored on Parse | WEEK 8
| As a User I want to be able to display other information such as age, preferred study location, and potentially other short descriptions so that other users have a better understanding of my preferences | High | 1 Day | Yes | UI looks appealing with specifications given by the Customer | WEEK 9
| As a User I want the color scheme to match UCSD colors so that it captures the essence of UCSD Triton Pride | High | 1 Day | Yes
| As a User I want the ability to add many classes so that I can have an accurate depiction of my profile | Medium-High | 3 Days | Yes
| As an admin, I want to be able to work with confirmation emails to further enhance security | Medium | 1 Day | No
WEEK 7 | As a User I want the ability to “Swipe Right” (left to right) so that I can indicate to another user that I am interested in studying with them | Highest | 1-3 Days | Yes
| As a User I want the ability to “Swipe Left” (right to left) so that I can indicate to another user that I am not interested in studying with them | Highest | 1-3 Days | Yes
| As a User I want to be able to see the the profile of other students and their classes so I can match with them | High | 1-2 Weeks | No
| As an admin, I want a way to display more relevant users first (such as people who are taking the same classes) so that my users are more satisfied with the overall application’s functionality | High | 1-2 Weeks | Yes
| As an admin, I want to be able to work with confirmation emails to further enhance security | Medium | 1 Day | No
| As an admin, I want a way to safeguard against and detect cases of academic integrity violations so that the application does not turn into a cheating platform | Low | 1-2 Weeks | No
| As a User I want to able to filter the profiles that are shown to me so that I don’t have to go through redundant matches when searching for a study partner | Medium-High | 1-2 Weeks | Yes
WEEK 8 | As an admin I want to restrict access so that only UCSD Students can access the app | High | <1 Day | No
| As a User I want to have an endorsement system similar to LinkedIn so that I can indicate to other users how credible I am as a study partner | Medium-High | 1 Week | No
| As a User I want the ability to report other users so that botters/advertisers/sketchy user are removed in a timely manner | Low | 1 Day | No
| As a User I want the ability to “Block” a user so that I can prevent other users who I do not want interacting with me/seeing my profile from doing so | Low | 1 Day | No
| As an admin, I want to be able to delete accounts so that botters/advertisers do not interfere with the usage of the app | Low | <1 Day | No
| As a User I want to have a Nightmode option so that when using the application at night there would be less strain on my eyes | Low | 1 Week | No
WEEK 9 | As a User I want some form of a messaging system so that I’m able to communicate with my matched study partner | Medium-High | 1 Week | Yes
| As a User I want the user Interface to be more vivid so that it is more appealing app to use | High | 1-3 Days | Yes
| As a User I want to be able to view my matched profiles and click them to see their profile page so that I can start messaging them | High | 1-3 Days | Yes
| As an User, I want the text to be blue and the buttons to be blue so that there is a theme and the app is more colorful | High | 1 Day | Yes